## Customer Page Test Plan
Application | http://retailm1.upskills.in/
Created By | Rahul, Hari, Sowmya, Sreedhar
Creation Date | 2021-10-09
Reviewed By | Prduct Owner
PreCondition | Good Network Connection, Web Browser
Reference | Retail Test Plan
Test scenario ID | Test scenario description | Expected result | Defect ID | Notes
TS1 | Verify functionality of Retail url | User should be able to open the customer page of retail url | N/A | Expected output will vary depends on the inputs
TS2 | Verify the homepage | User should be able to open the homepage | N/A | Expected output will vary depends on the inputs
TS3 | Verify the functionality of buttons and icons in home page | All the buttons and icons should work normally | D1,D2,D3,D4,D5 | Expected output will vary depends on the inputs
TS4 | Verify the Navigation functionality of the buttons inhomepage | All the Navigate buttons should work normally | D6 | Expected output will vary depends on the inputs
TS5 | Verify the product content page when quick view button is clicked | All the functionalities should work normally | D7,D8,D9 | Expected output will vary depends on the inputs
TS6 | Verify the functionality of login page | User should be able to open the login page | N/A | Expected output will vary depends on the inputs
TS7 | Verify the functionality of register page | User should be able to open the register page | D10 | Expected output will vary depends on the inputs
TS8 | Verify the functionality of login page& forgot password page with credentials | All the functionalities should work normally | D11 | Expected output will vary depends on the inputs
TS9 | Verify the functionality of user icon when user logged in | User functionality should work normally | D12 | Expected output will vary depends on the inputs
TS10 | Verify the functionality of user my account page | All the functionalities of account page should work properly | D13 | Expected output will vary depends on the inputs
TS11 | Verify the functionality of user's my order page | All the functionalities of my orders page should work properly | N/A | Expected output will vary depends on the inputs
TS12 | Verify the wish list | All the functionalities of wish list should work properly | D14 | Expected output will vary depends on the inputs
TS13 | Verify the cart page contents | All the functionalities of cart page should work properly | N/A | Expected output will vary depends on the inputs
TS14 | Verify the functionality of orders information in my order page | All the functionalities of my orders page should work properly | N/A | Expected output will vary depends on the inputs
TS15 | Verify the functionality of return button | All the functionalities of return button should work properly | N/A | Expected output will vary depends on the inputs
TS16 | Verify the functionality of user's my order page | All the functionalities of my orders page should work properly | N/A | Expected output will vary depends on the inputs
TS17 | Verify the functionality of check out page | All the functionalities of check out page should work properly | D15,D16,D17 | Expected output will vary depends on the inputs
TS18 | Verify the products page in home page | user should be able to verify the products in home page | D18,D19 | Expected output will vary depends on the inputs
TS19 | Verify the Review writing page | user should be able to verify the review page | D20 | Expected output will vary depends on the inputs
TS20 | Verify the functionality sitemap button | All the functionalities of check out page should work properly | D21,D22 | Expected output will vary depends on the inputs

## Wish-list and Cart Page
Application | http://retailm1.upskills.in/
Created By | Rahul, Hari, Sowmya, Sreedhar
Creation Date | 2021-10-09
Reviewed By | Prduct Owner
PreCondition | Good Network Connection, Web Browser
Reference | Retail Test Plan
Test Scenario ID | Test Scenario Desription | Test Case ID | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Defect ID | Status
TS11 | Verify the Wish-list page | TS11.1 | Check response when User clicks Wish-list Icon | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Wish-list Icon | E-Mail: rahulpadma999@gmail.com Password: 123456789 | It should re-direct the user Wish-list Page | Re-directed the User to Wish-list | N/A | Pass
|  | TS11.2 | Check whether Image,Name,Model,Stock,Unit-Price,Action Texts with respective details below them are displayed | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Wish-list Icon | E-Mail: rahulpadma999@gmail.com Password: 123456790 | It should display Product details | displayed Product details | N/A | Pass
|  | TS11.3 | Check whether Cart Icon is displayed & Functional | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Wish-list Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | 1.It should Display Cart Icon 2.product should be added to Cart when user clicks it 3.Pop-up should display showing "Cart-updated" | As Expected | N/A | Pass
|  | TS11.4 | Check whether 'X' Icon is displayed or not & functionality | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Wish-list Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | 1.It should Display 'X' Icon 2.product should be removed from Wish-list when user clicks it 3.Pop-up should display showing "You have Modified your Wish list! " 4.If no other products are present It should display Wish list is Empty. | As Expected | N/A | Pass
|  | TS11.5 | Check whether Continue button is displayed or not & functionality of it | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Wish-list Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Continue Button should display & it should Re-direct the user to My Account detail page when user Clicks it | As Expected | N/A | Pass
TS12 | Verify the Cart Page Contents | TS12.1 | Check the Content of Cart page when No items are added to the Cart | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should Display "Your Shopping Cart is Empty" Text. | "Your Shopping cart is Empty" Text is Displayed | N/A | Pass
|  | TS12.2 | Check whether Continue button is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should Display "Your Shopping Cart is Empty" Text. | "Your Shopping cart is Empty" Text is Displayed | N/A | Pass
|  | TS12.3 | Check whether Items added to cart are displayed. | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should display the Items Added to the Cart. | Items added to the cart are Displayed. | N/A | Pass
|  | TS12.4 | Check whether Image Text & Image of the product are displayed | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should Display Image text & Product Image | Some of the product Images are not displayed | D14 | Fail
|  | TS12.5 | Check whether Product name, Model,Quantity,Unit price,Total Text and their respective Details are displayed | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should Display Product name,Model,Quantity,Unit price,Total Text and their respective Details are displayed | As expected | N/A | Pass
|  | TS12.6 | Check whether 'Use Coupon code' text in a bar with Arrow button is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Text "Use Coupon code" should be aligned & displayed | Text "Use Coupon code" is displayed & aligned | N/A | Pass
|  | TS12.7 | Check whether the Text "Enter your Coupon code" is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Coupon code button | E-Mail: rahulpadma999@gmail.com Password: 123456791 | it should display 'Enter Your Coupon here' text. | As expected | N/A | Pass
|  | TS12.8 | Check whether the input bar of Coupon code is displaying and functional | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Coupon code button 7.Enter Coupon code | E-Mail: rahulpadma999@gmail.com Password: 123456791 Coupon code : RETAIL10 | it should display 'Enter Your Coupon here' text in the input bar & User should be able to Enter Text. | As expected | N/A | Pass
|  | TS12.9 | Check whether Apply coupon button is displayed or not & its functionality | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Coupon code button 7.Enter Coupon code 8.Click on Apply Coupon | E-Mail: rahulpadma999@gmail.com Password: 123456791 Coupon code : RETAIL10 | It should display a "Apply Coupon" button When the user Clicks it a Loading Symbol Animation Should be displayed | As expected | N/A | Pass
|  | TS12.10 | Check whether Apply coupon code is functional or not when the User enters a valid Coupon code | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Coupon code button 7.Enter Coupon code 8.Click on Apply Coupon | E-Mail: rahulpadma999@gmail.com Password: 123456791 Coupon code : 111 | when the User enters the coupon code & clicks on Apply Coupon It should Display "Success : Your Coupon discount has been apllied". | As expected | N/A | Pass
|  | TS12.11 | Check whether Apply coupon code is functional or not when the User enters a Invalid Coupon code | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Coupon code button 7.Enter Coupon code 8.Click on Apply Coupon | E-Mail: rahulpadma999@gmail.com Password: 123456791 Coupon code : RETAIL10 | when the User enters the coupon code & clicks on Apply Coupon It should Display "Warning :Coupon is either invalid, expired or reached its usage limit!" | As expected | N/A | Pass
|  | TS12.12 | Check whether 'Estimate Shipping & Taxes' text in a bar with Arrow button is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Text "'Estimate Shipping & Taxes" should be aligned & displayed | Text "Estimate Shipping & Taxes" is displayed & aligned | N/A | Pass
|  | TS12.13 | Check whether the Text "Enter your Destination to get a Shipping Estimate" is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should display 'Enter your Destination to get a Shipping Estimate' text. | As expected | N/A | Pass
|  | TS12.14 | Check whether the Text Country,Region/State,Post code are displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should display 'Country,Region/State,Post code' text with Red * mark for Country & State | As expected | N/A | Pass
|  | TS12.15 | Check whether the drop-down list Icon & input box are displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should display drop-down lists for Country,Region/State & Input text-box for Post code text with Red * mark for Country & State | As expected | N/A | Pass
|  | TS12.16 | Check whether the input bar for Post code & drop-down lists are functional | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | When the Clicks on drop-down button Options corresponding to the field are displayed & user should be able to Insert text for Post code | As expected | N/A | Pass
|  | TS12.17 | Check whether "Get Quotes" button is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button 7.Enter Country,State,Postcode | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | When the Clicks on drop-down button Options corresponding to the field are displayed & user should be able to Insert text for Post code | As expected | N/A | Pass
|  | TS12.18 | Check Functionality of "Get Quotes" button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button 7.Enter Country,State,Postcode | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | When the Clicks on Get Quotes button, respective content should be displayed | As expected | N/A | Pass
|  | TS12.19 | Check the contents when User Clicks on Get Quotes button. | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button 7.Enter Country,State,Postcode | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | Text "Please select the prefered Shipping method to use on this order." & Options should be displayed | As expected | N/A | Pass
|  | TS12.20 | Check the Apply Shipping button is dispalyed or not. | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button 7.Enter Country,State,Postcode | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | Apply Shipping button Should be displayed when user clicks on Get Quotes | Apply Shipping Button is displayed when User clicks on Get Quotes | N/A | Pass
|  | TS12.21 | Check the Functionality of Options(radio buttons) under Shipping method | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button 7.Enter Country,State,Postcode 8.Select any shipping method | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | User should be able to select one of the options under shipping methods. | As expected | N/A | Pass
|  | TS12.22 | Check the Functionality of Apply Shipping Button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Estimate Shipping & Taxes button 7.Enter Country,State,Postcode 8.Select any shipping method | E-Mail: rahulpadma999@gmail.com Password: 123456791 Country : India State : Delhi Post code : 500007 | Shipping method should eflect in the Total amount section | As expected | N/A | Pass
|  | TS12.23 | Check whether 'Use Gift Certificate' text in a bar with Arrow button is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Text "Use Gift Certificate" should be aligned & displayed | Text "Use Gift Certificate" is displayed & aligned | N/A | Pass
|  | TS12.24 | Check whether the Text "Enter Your Gift Certificate code here" is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Gift Certificate | E-Mail: rahulpadma999@gmail.com Password: 123456791 | It should display 'Use Gift Certtificate' text. | As expected | N/A | Pass
|  | TS12.25 | Check whether the input bar of "Enter Your Gift certificate" is displaying and functional | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Gift Certificate | E-Mail: rahulpadma999@gmail.com Password: 123456791 | it should display 'Enter Your Coupon here' text in the input bar & User should be able to Enter Text. | As expected | N/A | Pass
|  | TS12.26 | Check whether Apply Gift Certificate button is displayed or not & its functionality | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Gift Certificate 7.Enter Gift code | E-Mail: rahulpadma999@gmail.com Password: 123456791 Gift certificate : 12365 | It should display a "Apply Gift Certificate" button When the user Clicks it a Loading Symbol Animation Should be displayed | As expected | N/A | Pass
|  | TS12.27 | Check whether Apply Gift Certificate is functional or not when the User enters a valid Gift Certificate | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Gift Certificate 7.Enter Gift code | E-Mail: rahulpadma999@gmail.com Password: 123456791 Gift certificate : 12365 | when the User enters the coupon code & clicks on Apply Gift Certificate It should Display "Success : Your Gift Certificate discount has been applied". | As expected | N/A | Pass
|  | TS12.28 | Check whether Apply Gift Certificate is functional or not when the User enters a Invalid Gift Certificate | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Use Gift Certificate 7.Enter Gift code | E-Mail: rahulpadma999@gmail.com Password: 123456791 Gift certificate : ABCDFT | when the User enters the coupon code & clicks on Apply Gift Certificate It should Display "Warning :Gift Certificate is either invalid, expired or reached its usage limit!" | As expected | N/A | Pass
|  | TS12.29 | Check the functionality of Arrow buttons wherever applicable | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | When User Clicks on arrow button it should drop-down the respective content with change in arrow direction | As expected | N/A | Pass
|  | TS12.30 | Check whether Billing details section, with the corresponding values displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | user should be able to see Sub-total,Total,any other discount with respective values corresponding to it. | As expected | N/A | Pass
|  | TS12.31 | Check whether Continue Shooping & Checkout buttons are displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Continue Shooping & Checkout buttons should be aligned & displayed | Continue Shooping & Checkout buttons are displayed & aligned. | N/A | Pass
|  | TS12.32 | Check the Functionality of Continue Shooping button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on Conitue Shopping | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Upon Clicking Continue Shopping Button User Should be Re-directed to the Home Page. | User re-directed to Home Page when Continue Shopping Button is clicked. | N/A | Pass
|  | TS12.33 | Check the Functionality of Checkout button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on User Icon 3.Click on Login/Register 4.Enter Credentials & Click on Login 5.Click on Cart Icon 6.Click on CheckOut | E-Mail: rahulpadma999@gmail.com Password: 123456791 | Upon Clicking CheckOut Button User Should be Re-directed to the Checkout Page. | User re-directed to Checkout Page when Checkout Button is clicked. | N/A | Pass
TS13 | Verify the Functionality of View Your Order History in User's My Orders Page | TS13.1 | Check whether the My Orders text is diplaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Orders | N/A | My Orders text should be displayed | My Orders text is displayed | N/A | Pass
|  | TS13.2 | The text "View your Order History" is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.View your Order History | N/A | The text "View your Order History" should be displayed | The text "View your Order History" is displayed | N/A | Pass
|  | TS13.3 | Check whether the Product Details(Order Id, Customer, No. of Products, Status, Total, Date Added) is displaying or not when View your Order History is clicked | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History | N/A | Product Details(Order Id, Customer, No. of Products, Status, Total, Date Added) Should be displayed | Product Details(Order Id, Customer, No. of Products, Status, Total, Date Added) is displayed | N/A | Pass
|  | TS13.4 | Check whether Eye Icon and Continue Button is Displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History | N/A | Eye Icon and Continue Button should be Displayed | Eye Icon and Continue Button is Displayed | N/A | Pass
|  | TS13.5 | Check the Response when User clicks on Eye Icon | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Icon | N/A | It Should be Navigate to the Order Detail page | It is Navigated to the Order Detail page | N/A | Pass
|  | TS13.6 | Check the Response of Continue Button When User Clicks on it | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Continue Button | N/A | It Should be Navigate to the My Account page | It is Navigated to the My Account page | N/A | Pass
TS14 | Verify the Functionality of Order Information Page in My orders | TC14.1 | Check whether the Order Details(Orde Id, Payment Method, Date added, Shipping Method) is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button | N/A | Order Details(Orde Id, Payment Method, Date added, Shipping Method) Should be Displayed | Order Details(Orde Id, Payment Method, Date added, Shipping Method) is Displayed | N/A | Pass
|  | TC14.2 | Check whether the Payment address and Shipping address is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button | N/A | Payment address and Shipping address Should be Displayed | Payment address and Shipping address is Displayed | N/A | Pass
|  | TC14.3 | Check whether the Product name, Model, Quantity, Price, Total and (Sub total, Free Shipping, Total)are Displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button | N/A | Product name, Model, Quantity, Price and Total and ((Sub total, Free Shipping, Total) Should be Displayed | Product name, Model, Quantity, Price, Total (Sub total, Free Shipping, Total) is Displayed | N/A | Pass
|  | TC14.4 | Check Whether the Cart Button and Return Icons are Displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button | N/A | Cart Button and Return Icons Should be Displayed | Cart Button and Return Icons are Displayed | N/A | Pass
|  | TC14.5 | Check Whether the Same Product is Adding to Cart and Getting Pop up or not When User clicks on Cart Button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Cart Button | N/A | Product Should be added to the Cart and Pop Should be Display | Product added to the Cart and Pop Displayed | N/A | Pass
TS15 | Verify the Functionality of Return Button | TC15.1 | Check Whether the Text "Please complete the form below to request an RMA number" is Displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button | N/A | Text "Please complete the form below to request an RMA number" Should be Displayed | Text "Please complete the form below to request an RMA number" is Displayed | N/A | Pass
|  | TC15.2 | Check whether the text(Your Order Information, first name, last name, email,telephone, Order Id, Order Date) is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button | N/A | The text(Your Order Information, first name, last name, email,telephone, Order Id, Order Date) should be displayed | The text(Your Order Information, first name, last name, email,telephone, Order Id, Order Date) is displayed | N/A | Pass
|  | TC15.3 | Check whether the text boxes are displaying or not with previously entered details | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on Edit your account Information | N/A | The text boxes should be displayed with previously entered details | The text boxes are displayed with previously entered details | N/A | Pass
|  | TC15.4 | Check whether the Text Box is Showing Error or not when user Unfill the Data in any Text Box | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button 11.Enter Data Only in Some Text Boxes 12.Click on Continue | N/A | Text Box Should Show Error when user Unfill the Data in any Text Box | Text Box is Showing Error when user Unfill the Data in any Text Box | N/A | Pass
|  | TC15.5 | Check Response of Calendar Button When User Clicks on it | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button 11.Click on Calender Button | N/A | Calender Should Display | Calender is Displayed | N/A | Pass
|  | TC15.6 | Check Response of Calendar Page When User Clicks on it and It is updating or not In Text Box | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button 11.Click on Calender Button 12.Click on Calender Page | N/A | Data Should be Update in Text Box | Data is Updated in Text Box | N/A | Pass
|  | TC15.7 | Check whether the text(Product Information, Product name, Product Code, Quantity) is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button | N/A | The text(Product Information, Product name, Product Code, Quantity) Should be Displayed | The text(Product Information, Product name, Product Code, Quantity) is Displayed | N/A | Pass
|  | TC15.8 | Check whether the Reason for Return Text (Subheading With Radio Buttons)is Displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button | N/A | Dead on Arrival, Faulty Please Supply Details, Order Error, Other Please Supply Details, Received wrong item | As Expected | N/A | Pass
|  | TC15.9 | Check whether the Text is selecting or not When user clicks on Corresponding Radio button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button 11.Click on Radio Button | N/A | The Text Should be Selected when Corresponding Radio button is Selected | As Expected | N/A | Pass
|  | TC15.10 | Check whether the text "Product is Opened" (Yes and No with Radio Button) is Displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button | N/A | The Text Should be Selected when Corresponding Radio button is Selected | As Expected | N/A | Pass
|  | TC15.11 | Check whether the Text is selecting or not When user clicks on Corresponding Radio button | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button 11.Click on Radio Button | N/A | The Text Should be Selected when Corresponding Radio button is Selected | As Expected | N/A | Pass
|  | TC15.12 | Check whether the text "Faculty or Orther Details" and A box is displaying or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button | N/A | The text"Faulty or Orther Details" and A box Should be Displayed | The text"Faculty or Orther Details" and A box is Displayed | N/A | Pass
|  | TC15.13 | Check whether the text box is accepting text or not when user enter the Data | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Return Button 11.Enter text in Text Box | Input Data: rahul | The text"Faculty or Orther Details" and A box Should be Displayed | The text"Faculty or Orther Details" and A box is Displayed | N/A | Pass
|  | TC15.14 | Check Whether the Submitt Button is Displaying and Navigating or not | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Submitt Button | N/A | Submitt Button Should Display and Navigate | Submitt Button is Diplayed and Navigated | N/A | Pass
|  | TC15.15 | Check Response of Submitt Button when User Clicks on it | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Submitt Button | N/A | It Should Display Content like "Thank you for submitting your return request. Your request has been sent to the relevant department for processing" and "Thank you for submitting your return request. Your request has been sent to the relevant department for processing" and Continue Button | As Expected | N/A | Pass
|  | TC15.16 | Check Response of Continue Button when User Clicks on it | 1. Naviagte to http://retailm1.upskills.in/ 2.Click on the User Icon 3.Click on the Login/Register Button 4.Enter Credentials 5.Click on Login 6. Enter the credentials 7.Click on My Account 8. Click on View your Order History 9.Click on Eye Button 10.Click on the Submitt Button | N/A | It should Redirect to Home Page | It Is Redirected to the Home Page | N/A | Pass