## Retail Test Plan(Admin)
Application | http://retailm1.upskills.in/admin/
Name | Retail Admin Test Plan
Created By | Sai Kaushik, Soundarya, Venkatesh
Creation Date | 2021-10-04
Reviewed By | Product Owner
Test scenario ID | Test Scenario Description | Expected Result | Defect ID | Notes
TS1 | Verify login functionality with existing account | User should be able to login to the admin page of Retail application | N/A | Expected Output will vary depends on the inputs
TS2 | Verify forgotten password | User should be able to reset the password | N/A | Expected Output will vary depends on the inputs
TS3 | Verify Webpage Functionalities | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS4 | Verify the Dashboard UI | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS5 | Verify the Dashboard Functionalities | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS6 | Verify the Catalog UI | UI should be as expected | N/A | Expected Output will vary depends on the inputs
TS7 | Verify the catalog functionalities for Categories | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS8 | Verify the catalog functionalities for Products | All the functionalities should work normally | DF01 | TCC25 - No mandatory fields to fetch desired product,so if there is one mandatory field we can get accurate product result
TS9 | Verify the catalog functionalities for Recurring Profiles | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS10 | Verify the catalog functionalities for Filters | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS11 | Verify the catalog functionalities for Attributes | All the functionalities should work normally | DF02 | TCC79 - Under Add New Attribute the attribute group field is not marked as mandatory
|  |  | DF03 | TCC80 - Under Add New Attribute the attribute group field is not marked as mandatory
TS12 | Verify the catalog functionalities for Options | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS13 | Verify the catalog functionalities for Manfacturers | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS14 | Verify the catalog functionalities for Downloads | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS15 | Verify the catalog functionalities for reviews | All the functionalities should work normally | DF04 | TCC131- Admin Is not getting suggestions when typing product name under review list
|  |  | DF05 | TCC132 - No mandatory fields to fetch desired product, so if there is one mandatory field we can get accurate Review result
TS16 | Verify the catalog functionalities for Information | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS17 | Verify the Sales functionalities for Orders | All the functionalities should work normally | DF06 | TCS5 - No mandatory fields to fetch desired ordered product, so if there is one mandatory field we can get accurate Order result
TS18 | Verify the Sales functionalities for Recurring Profiles | All the functionalities should work normally | DF07 | TCS38 - No mandatory fields to fetch desired order,so if there is one mandatory field we can get accurate result for the recuuring profile
TS19 | Verify the Sales functionalities for Returns | All the functionalities should work normally | DF08 | TCS43 - No mandatory fields to fetch detail regarding product return, so if there is one mandatory field we can get accurate result on Returns
TS20 | Verify the Sales functionalities for Gift Vouchers | All the functionalities should work normally | DF09 | TCS73 - Admin is not able to send the Gift Vouchers either to single or multiple orders.
TS21 | Verify the Customers UI | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS22 | Verify the Customer functionalities for Customers | All the functionalities should work normally | DF10 | TCU9 - No mandatory fields to fetch details of customer, so if there is one mandatory field we can get accurate result on Customers
TS23 | Verify the Customers functionalities for customer groups | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS24 | Verify the customers functionalities for Custom fields | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS25 | Verify the marketing UI | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS26 | Verify the marketing functionalities for marketing | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS27 | Verify the marketing functionalities for Affiliates | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS28 | Verify the marketing funcionalities for Coupons | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS29 | Verify the marketing functionalities for Mail | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS30 | Verify the Reports UI | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS31 | Verify the Reporting functionalities for Sales | All the functionalities should work normally | DF11 | TCR13 - No mandatory fields to fetch desired coupons,so if there is one mandatory field we can get accurate result on Sales Coupons
TS32 | Verify the Reporting functionalities for Products | All the functionalities should work normally | N/A | Expected Output will vary depends on the inputs
TS33 | Verify the Reporting functionalities for Customers Online | All the functionalities should work normally | DF12 | TCR26 - No mandatory fields to fetch customers details, so if there is one mandatory field we can get accurate result on list of Customers
|  |  | DF13 | TCR28 - No mandatory fields to fetch details on customer's order,so if there is one mandatory field we can get accurate result on Customer Orders
|  |  | DF14 | TCR30 - No mandatory fields to fetch customer reward points, so if there is one mandatory field we can get accurate result on Reward Points
|  |  | DF15 | TCR32 - No mandatory fields to fetch details on customer credit list, so if there is one mandatory field we can get accurate result on credits
TS34 | Verify the Reporting functionalities for Marketing | All the functionalities should work normally | DF16 | TCR34 - No mandatory fields to fetch for desired products in market,so if there is one mandatory field we can get accurate Marketing results
|  |  | DF17 | TCR39 - No mandatory fields to fetch affiliate activities ,so if there is one mandatory field we can get accurate details on Affiliate Activities

## Sales Functionalities
Application | http://retailm1.upskills.in/admin/
Created By | Sai Kaushik, Soundarya, Venkatesh
Creation Date | 2021-10-04
Reviewed By | Prduct Owner
PreCondition | Good Network Connection
Reference | Amazon
Test Scenario ID | Test Scenario Desription | Test Case ID | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Defect ID
TS17 | Verify the Sales functionalities for Orders | TCS1 | Check response for Orders | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders | Username: admin Password: admin@123 | Order list page is visible | Order list page is visible | Pass | N/A
|  | TCS2 | Check whether order ID can be viewed in numerical order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders | Username: admin Password: admin@123 | Order ID can be viewed either in decreasing or increasing order | Order ID can be viewed either in decreasing or increasing order | Pass | N/A
|  | TCS3 | Check whether admin is able to enter the details of the ordered product | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders and enter the details | Username: admin Password: admin@123 | Admin should be able to fill the Order ID, Customer Name, Order Status, Total Amount, Date added and Modified date details in the order list page | Admin should be able to fill the Order ID, Customer Name, Order Status, Total Amount, Date added and Modified date details in the order list page | Pass | N/A
|  | TCS4 | Check response for suggestions while filling the required fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders and enter the details 6. Click on filter button | Username: admin Password: admin@123 Order Id - 1 Customer- Rahul Status-enabled Amount - | Suggestions are displayed when admin fills the fields | Suggestions are displayed when admin fills the fields | Pass | N/A
|  | TCS5 | Check whether atleast one field is mandatory to get the exact detail of the ordered product | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. Click on filter button | Username: admin Password: admin@123 | Atleast one field should be mandatoy | Atleast one field should be mandatoy | Fail | DF06
|  | TCS6 | Check the functionality of "Add New" Button in Order List page | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button | Username: admin Password: admin@123 | Add Order page should be opened | Add Order page should be opened | Pass | N/A
|  | TCS7 | Check response of the form "Add Order" | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button | Username: admin Password: admin@123 | Admin should be able to access the Customer Details tag and fill the required fields in the form. Also, Products, Payment Details, Shipping Details and Totals tags must be diabled | Admin should be able to access the Customer Details tag and fill the required fields in the form. Also, Products, Payment Details, Shipping Details and Totals tags must be diabled | Pass | N/A
|  | TCS8 | Check the response for mandatory fields in Customer Details subtag under Add Order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button and enter the details 7. Click on Continue | Username: admin Password: admin@123 First Name: Rahul Last Name: Padma E-mail: rahul@gmail.com Telephone: 1234567890 | Mandatory fields in Customer Details subtag under Add Order are filled and admin can proceed to Products tag | Mandatory fields in Customer Details subtag under Add Order are filled and admin can proceed to Products tag | Pass | N/A
|  | TCS9 | Check the response for mandatory fields if First Name is not filled in Customer Details form | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button and enter the details 7. Click on Continue | Username: admin Password: admin@123 First Name: Last Name: Padma E-mail: rahul@gmail.com Telephone: 1234567890 | First Name must be between 1 and 32 characters! | First Name must be between 1 and 32 characters! | Pass | N/A
|  | TCS10 | Check the response for mandatory fields if Last Name is not filled in Customer Details form | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button and enter the details 7. Click on Continue | Username: admin Password: admin@123 First Name: Rahul Last Name: E-mail: rahul@gmail.com Telephone: 1234567890 | Last Name must be between 1 and 32 characters! | Last Name must be between 1 and 32 characters! | Pass | N/A
|  | TCS11 | Check the response for mandatory fields if E-mail is not filled in Customer Details form | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button and enter the details 7. Click on Continue | Username: admin Password: admin@123 First Name: Rahul Last Name: Padma E-mail: Telephone: 1234567890 | E-Mail Address does not appear to be valid! | E-Mail Address does not appear to be valid! | Pass | N/A
|  | TCS12 | Check the response for mandatory fields if Telephone is not filled in Customer Details form | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button and enter the details 7. Click on Continue | Username: admin Password: admin@123 First Name: Rahul Last Name: Padma E-mail: rahul@gmail.com Telephone: | Telephone must be between 3 and 32 characters! | Telephone must be between 3 and 32 characters! | Pass | N/A
|  | TCS13 | Check the response for optional fields in Products subtag under Product tag | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Products tag 8. Click on Add Product | Username: admin Password: admin@123 Product Name: Ear Rings Sort Order: 1 | Choose the product from the available product list and is updated in product table | Choose the product from the available product list and is updated in product table | Pass | N/A
|  | TCS14 | Check the response when the product, which is not from the product list, is choosen | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Products tag 8. Click on Add Product | Username: admin Password: admin@123 Product Name: testKaushik Sort Order: 2 | Products marked with *** are not available in the desired quantity or not in stock! | Products marked with *** are not available in the desired quantity or not in stock! | Pass | N/A
|  | TCS15 | Check the response for mandatory fields in Vouchers subtag under Product tag | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Products tag 8. Click on Add Voucher and continue | Username: admin Password: admin@123 Recipient's Name: Sondarya V S Recipient's E-mail: sound@gmail.com Sender's Name: Venkat Sender's E-mail: venky@gmail.com Gift Certificate: Theme Amount: 100 | Mandatory fields in Vouchers subtag are filled and newly added voucher is updated in product table and admin can proceed to Payment Details tag | Mandatory fields in Vouchers subtag are filled and newly added voucher is updated in product table and admin can proceed to Payment Details tag | Pass | N/A
|  | TCS16 | Check the response for mandatory fields in Payment Details tag | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Payment Details 8. Click on Continue | Username: admin Password: admin@123 First Name: Soundarya Last Name: V S Address 1: XYZ City: ABC Country: India Region / State: Karnataka | Mandatory fields in Payment Details tag are filled and admin can proceed to Shipping Details tag | Mandatory fields in Payment Details tag are filled and admin can proceed to Shipping Details tag | Pass | N/A
|  | TCS17 | Check the response for mandatory fields in Shipping Details tag | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Shipping Details 8. Click on Continue | Username: admin Password: admin@123 First Name: Soundarya Last Name: V S Address 1: XYZ City: ABC Country: India Region / State: Karnataka | Mandatory fields in Shipping Details tag are filled and admin can proceed to the last tag i.e., Totals | Mandatory fields in Shipping Details tag are filled and admin can proceed to the last tag i.e., Totals | Pass | N/A
|  | TCS18 | Check whether product and voucher amount is totalled in Totals tag | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Totals tag 8. Click on Continue | Username: admin Password: admin@123 | Product and voucher amount is totalled in Totals tag | Product and voucher amount is totalled in Totals tag | Pass | N/A
|  | TCS19 | Check response when product and vouchers are not added | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Totals tag 8. Click on Continue | Username: admin Password: admin@124 | The shipping method field is disabled and the payment method should be "Free Checkout" | The shipping method field is disabled and the payment method should be "Free Checkout" | Pass | N/A
|  | TCS20 | Check the dropdown option for shipping methods in the order details | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Totals tag 8. Click on Save | Username: admin Password: admin@123 Shipping Method: Free shipping | Success: Shipping method has been set! | Success: Shipping method has been set! | Pass | N/A
|  | TCS21 | Check the dropdown option for Payment methods in the order details | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Totals tag 8. Click on Save | Username: admin Password: admin@123 Payment Method: Cash on Delivery | Success: Payment method has been set! | Success: Payment method has been set! | Pass | N/A
|  | TCS22 | Check the response for mandatory fields if Shipping method is not selected in Order Details form | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Totals tag 8. Click on Save | Username: admin Password: admin@123 Shipping Method: Payment Method: Cash on Delivery | Warning: Shipping method required! | Warning: Shipping method required! | Pass | N/A
|  | TCS23 | Check the response for mandatory fields if Payment method is not selected in Order Details form | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Proceed towards Totals tag 8. Click on Save | Username: admin Password: admin@123 Shipping Method: Free shipping Payment Method: Cash on Delivery | Warning: Payment method required! | Warning: Payment method required! | Pass | N/A
|  | TCS24 | Check whether order list is updated when customer makes a new order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. View Orders List | Username: admin Password: admin@122 | Order list is updated ! | Order list is updated ! | Pass | N/A
|  | TCS25 | Check whether admin is able to change the status of the placed order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Edit button 7. Proceed towards Totals tag 8. Select the appropriate option under the Order Status dropdown | Username: admin Password: admin@123 | Updated status is reflected for customer order | Updated status is reflected for customer order | Pass | N/A
|  | TCS26 | Check whether the order via customer name is added to the order list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List click on Add new button 7. Click on Save button | Username: admin Password: admin@123 | New order is added to the order list after clicking on the save button | New order is added to the order list after clicking on the save button | Pass | N/A
|  | TCS27 | Check whether admin is able to view the exisiting order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Order List click on View Button | Username: admin Password: admin@123 | Admin is able to view the exisiting order | Admin is able to view the exisiting order | Pass | N/A
|  | TCS28 | Check whether admin can add order history of a particular customer under view button in order list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Order List click on View Button | Username: admin Password: admin@123 | Admin can add order history of a particular customer under view button in order list | Admin can add order history of a particular customer under view button in order list | Pass | N/A
|  | TCS29 | Check whether Order Hisotry table is updated on adding the new history of a particular customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Order List click on View Button 7. Click on Add History | Username: admin Password: admin@123 Comment: Testing | Success: You have modified orders | Success: You have modified orders | Pass | N/A
|  | TCS30 | Check the function of Print Invoice and Shipping List buttons under view button in the order list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Order List click on View Button 7. Click on Print Invoice/Print Shippling List | Username: admin Password: admin@123 | Admin is able to take the printouts of the invoice and shipping details of the order | Admin is able to take the printouts of the invoice and shipping details of the order | Pass | N/A
|  | TCS31 | Check the function of Edit button in the order list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Order List click on Edit Button | Username: admin Password: admin@123 | Admin is redirected to the add order page and can edit the form | Admin is redirected to the add order page and can edit the form | Pass | N/A
|  | TCS32 | Check whether admin is able to delete single exisiting order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List select the single checkbox 7. Click on Delete button | Username: admin Password: admin@123 | Single Exisiting order is deleted | Single Exisiting order is deleted | Pass | N/A
|  | TCS33 | Check whether admin is able to delete multiple exisiting order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List select the multiple checkboxes 7. Click on Delete button | Username: admin Password: admin@123 | Multiple Exisiting orders are deleted | Multiple Exisiting orders are deleted | Pass | N/A
|  | TCS34 | Check whether admin can take invoice and shipping list print of single or mutiple orders at once | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In Orders List select the single/multiple checkboxes 7. Click on Print Invoice / Print Shipping List button | Username: admin Password: admin@123 | Admin can take invoice and shipping list print of single or mutiple orders at once | Admin can take invoice and shipping list print of single or mutiple orders at once | Pass | N/A
TS18 | Verify the Sales functionalities for Recurring Profiles | TCS35 | Check response for Recurring Profiles | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Recurring Profiles | Username: admin Password: admin@123 | Recurring Order page is visible | Recurring Order page is visible | Pass | N/A
|  | TCS36 | Check whether admin is able to enter the details for Recurring Orders | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Recurring Profiles and enter the details | Username: admin Password: admin@123 | Admin should be able to fill the Recurring ID, Order ID, Customer Name, Order Status, Date added and Payment Reference details in the Recurring order list page | Admin should be able to fill the Recurring ID, Order ID, Customer Name, Order Status, Date added and Payment Reference details in the Recurring order list page | Pass | N/A
|  | TCS37 | Check response for suggestions while filling the required fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Recurring Profiles and enter the details 6. Click on filter button | Username: admin Password: admin@123 Customer - Rahul Status-enabled | Suggestions are displayed when admin fills the fields | Suggestions are displayed when admin fills the fields | Pass | N/A
|  | TCS38 | Check whether atleast one field is mandatory to get the exact detail of the Recurring order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Recurring Profiles 6. Click on filter button | Username: admin Password: admin@123 | Atleast one field should be mandatoy | Atleast one field should be mandatoy | Fail | DF07
TS19 | Verify the Sales functionalities for Returns | TCS39 | Check response for Returns | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns | Username: admin Password: admin@123 | Product Return List page is visible | Product Return List page is visible | Pass | N/A
|  | TCS40 | Check whether Return ID can be viewed in numerical order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns | Username: admin Password: admin@123 | Return ID can be viewed either in decreasing or increasing order | Return ID can be viewed either in decreasing or increasing order | Pass | N/A
|  | TCS41 | Check whether admin is able to enter the details for Product Return List | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns and enter the details | Username: admin Password: admin@123 | Admin should be able to fill the Retuen ID, Order ID, Customer Name, Product, Model, Return Status, Date added and modified date details in the Product Return list | Admin should be able to fill the Retuen ID, Order ID, Customer Name, Product, Model, Return Status, Date added and modified date details in the Product Return list | Pass | N/A
|  | TCS42 | Check response for suggestions while filling the required fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns and enter the details 6. Click on filter button | Username: admin Password: admin@123 Customer - Rahul Order ID - 1 Status-enabled | Suggestions are displayed when admin fills the fields | Suggestions are displayed when admin fills the fields | Pass | N/A
|  | TCS43 | Check whether atleast one field is mandatory to get the exact detail for returning the product | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. Click on filter button | Username: admin Password: admin@123 | Atleast one field should be mandatoy | Atleast one field should be mandatoy | Fail | DF08
|  | TCS44 | Check the function of "Add New" Button in Product Return List | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product Return List click on Add new button | Username: admin Password: admin@123 | Order information page should be opened | Order information page should be opened | Pass | N/A
|  | TCS45 | Check the response for mandatory fields in General subtag under Add Product Return | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product Return List click on Add new button and enter the details 7. Click on Save/Cancel button | Username: admin Password: admin@123 Order ID: 436 First Name: Rahul Last Name: Padma E-mail: sound@gmail.com Telephone: 1234567890 Product: Engagement Ring Model: SKU-013 | Success: You have modified returns! | Success: You have modified returns! | Pass | N/A
|  | TCS46 | Check whether the product to be returned is added to the Product Return list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product return list click on Add new button 7. Click on Save/Cancel button | Username: admin Password: admin@123 | The product to be returned is added to the Product Return list after clicking on the save button | The product to be returned is added to the Product Return list after clicking on the save button | Pass | N/A
|  | TCS47 | Check whether when customer returns an order, Order ID and Return ID are updated in product return list | 1. Navigate to http://retailm1.upskills.in/ 2. Enter username and password 3. Click on Login 4. Click on My Orders 5. Click on View your Order History | E-mail ID: admintest@gmail.com Password: admin@124 | Customer returned product is updated in product return list | Customer returned product is updated in product return list | Pass | N/A
|  | TCS48 | To perform refund action check response of return action status under genaral tag | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product return list click on Edit button 7. Under genersal change the status to refunded | Username: admin Password: admin@123 | Return action is updated to refunded | Return action is updated to refunded | Pass | N/A
|  | TCS49 | Check whether when refund is completed change the "Return Status" from Awaiting Products to completed | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product return list click on Edit button 7. Under change the status to refunded | Username: admin Password: admin@123 | Return status is updated to completed | Return status is updated to completed | Pass | N/A
|  | TCS50 | After updating "Return Action" and "Return Status" change the order status under Orders accordingly | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Orders 6. In order list click on Edit button on which you want to change the order status 7. Proceed towards totals tag 8. Change the order status accordingly | Username: admin Password: admin@123 | Order Status is changed and notified to the customer. Also, updated in the order list | Order Status is changed and notified to the customer. Also, updated in the order list | Pass | N/A
|  | TCS51 | Check the function of Edit button in the Product Return list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product Return List click on Edit Button | Username: admin Password: admin@123 | Admin is redirected to the Edit Product Return page and can edit the form | Admin is redirected to the Edit Product Return page and can edit the form | Pass | N/A
|  | TCS52 | Check whether admin is able to delete single exisiting Product Return | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product Return List select the single checkbox 7. Click on Delete button | Username: admin Password: admin@123 | Single Exisiting Product Return is deleted | Single Exisiting Product Return is deleted | Pass | N/A
|  | TCS53 | Check whether admin is able to delete multiple exisiting Product Return | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product Return List select the multiple checkboxes 7. Click on Delete button | Username: admin Password: admin@123 | Multiple Exisiting Product Return are deleted | Multiple Exisiting Product Return are deleted | Pass | N/A
TS20 | Verify the Sales functionalities for Gift Vouchers | TCS54 | Check the response of Gift Vouchers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers | Username: admin Password: admin@123 | Drop down menu will be opened with options Gift Vouchers and Voucher Themes | Drop down menu will be opened with options Gift Vouchers and Voucher Themes | Pass | N/A
|  | TCS55 | Check the response of Vouchers Theme | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Vouchers Theme | Username: admin Password: admin@123 | Voucher Theme List page should be opened | Voucher Theme List page should be opened | Pass | N/A
|  | TCS56 | Check the function of "Add New" Button in Voucher Theme List page | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Vouchers Theme 7. Click on Add New button | Username: admin Password: admin@123 | Add Vouchers Theme page should be opened | Add Vouchers Theme page should be opened | Pass | N/A
|  | TCS57 | Check the response for mandatory field in Add Voucher Theme under Voucher Themes | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Vouchers Theme 7. Click on Add New button 8. Click on Save/Cancel button | Username: admin Password: admin@123 Voucher Theme Name: MiniTest Image: popup2.jpg | Success: You have modified voucher themes! | Success: You have modified voucher themes! | Pass | N/A
|  | TCS58 | Check whether the Voucher Theme is added to the Voucher Theme list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product return list click on Add new button 7. Click on Save/Cancel button | Username: admin Password: admin@123 | The Voucher Theme is added to the Voucher Theme list after clicking on the save button | The Voucher Theme is added to the Voucher Theme list after clicking on the save button | Pass | N/A
|  | TCS59 | Check the response for mandatory field if Voucher Theme Name is not filled in Add Voucher Theme | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Vouchers Theme 7. Click on Add New button 8. Click on Save/Cancel button | Username: admin Password: admin@123 Voucher Theme Name: Image: popup2.jpg | Voucher Theme Name must be between 3 and 32 characters! | Voucher Theme Name must be between 3 and 32 characters! | Pass | N/A
|  | TCS60 | Check the response for mandatory field if image is not uploaded | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Vouchers Theme 7. Click on Add New button 8. Click on Save/Cancel button | Username: admin Password: admin@123 Voucher Theme Name: MiniTest Image: | Image required! | Image required! | Pass | N/A
|  | TCS61 | Check the function of Edit button in the Voucher Theme list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Vouchers Theme 7. Click on Edit button in Voucher Theme List 8. Click on Save/Cancel button | Username: admin Password: admin@123 | Admin is redirected to the Edit Voucher Theme page and can edit the form | Admin is redirected to the Edit Voucher Theme page and can edit the form | Pass | N/A
|  | TCS62 | Check whether admin is able to delete single exisiting Voucher Theme | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6.Click on Voucher Theme 7. In Voucher ThemeList select the single checkbox 8. Click on Delete button | Username: admin Password: admin@123 | Single Exisiting Voucher Theme is deleted | Single Exisiting Voucher Theme is deleted | Pass | N/A
|  | TCS63 | Check whether admin is able to delete multiple exisiting Voucher Themes | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6.Click on Voucher Theme 7. In Voucher ThemeList select the multiple checkboxes 8. Click on Delete button | Username: admin Password: admin@123 | Multiple Exisiting Voucher Themes are deleted | Multiple Exisiting Voucher Themes are deleted | Pass | N/A
|  | TCS64 | Check the response of Gift Vouchers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers | Username: admin Password: admin@123 | Gift Vouchers List page should be opened | Gift Vouchers List page should be opened | Pass | N/A
|  | TCS65 | Check the function of "Add New" Button in Gift Vouchers List page | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Add New button | Username: admin Password: admin@123 | Add Gift Voucher page should be opened | Add Gift Voucher page should be opened | Pass | N/A
|  | TCS66 | Check the response for mandatory field in Add Gift Voucher under Gift Vouchers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Add New button 7. Click on Save/Cancel button | Username: admin Password: admin@123 Code: Mini123 From Name: Kaushik From E-mail: sridarakaushik666@gmail.com To Name: Sound To E-mail: soundarya126@gmail.com Amount:100 | Success: You have modified vouchers! | Success: You have modified vouchers! | Pass | N/A
|  | TCS67 | Check whether Gift Voucher is added to the Gift Voucher list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Returns 6. In Product return list click on Add new button 7. Click on Save/Cancel button | Username: admin Password: admin@123 | The new Gift Voucher is added to the Gift Voucher list after clicking on the save button | The new Gift Voucher is added to the Gift Voucher list after clicking on the save button | Pass | N/A
|  | TCS68 | Check response if mandatory fields are not filled in Add Gift Voucher under Gift Vouchers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Vouchers 6. Click on Add New button 7. Click on Save/Cancel button | Username: admin Password: admin@123 Code: From Name: From E-mail: To Name: To E-mail: Amount: | Warning! Code must be between 3 and 10 characters! Your Name must be between 1 and 64 characters! E-Mail Address does not appear to be valid! Recipient's Name must be between 1 and 64 characters! E-Mail Address does not appear to be valid! Amount must be greater than or equal to 1! | Warning! Code must be between 3 and 10 characters! Your Name must be between 1 and 64 characters! E-Mail Address does not appear to be valid! Recipient's Name must be between 1 and 64 characters! E-Mail Address does not appear to be valid! Amount must be greater than or equal to 1! | Pass | N/A
|  | TCS69 | Check the functionality of View Order button in Gift Voucher list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Voucher 6. In Gift Voucher List click on View Order Button | Username: admin Password: admin@123 | The gift vouchers added during product ordering process can be viewed here | The gift vouchers added during product ordering process can be viewed here | Pass | N/A
|  | TCS70 | Check the functionality of Edit button in the Gift Voucher list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Voucher 6. In Gift Voucher List click on Edit Button | Username: admin Password: admin@123 | Admin is redirected to the Edit Gift Voucher page and can edit the form | Admin is redirected to the Edit Gift Voucher page and can edit the form | Pass | N/A
|  | TCS71 | Check whether admin is able to delete single exisiting Gift Voucher | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Voucher 6. In Gift Voucher List select the single checkbox 7. Click on Delete button | Username: admin Password: admin@123 | Single Exisiting Gift Voucher is deleted | Single Exisiting Gift Voucher is deleted | Pass | N/A
|  | TCS72 | Check whether admin is able to delete multiple exisiting Gift Voucher | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Voucher 6. In Gift Voucher List select the multiple checkboxes 7. Click on Delete button | Username: admin Password: admin@123 | Multiple Exisiting Gift Voucher are deleted | Multiple Exisiting Gift Voucher are deleted | Pass | N/A
|  | TCS73 | Check whether admin can send Gift Vouchers either to single or mutiple orders | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Sales 5. Click on Gift Voucher 6. In Gift VoucherList select the single/multiple checkboxes 7. Click on Send button | Username: admin Password: admin@123 | Admin can send Gift Vouchers either to single or mutiple orders | Admin can send Gift Vouchers either to single or mutiple orders | Fail | DF09

## Customer Functionalities
Application | http://retailm1.upskills.in/admin/
Created By | Sai Kaushik, Soundarya, Venkatesh
Creation Date | 2021-10-04
Reviewed By | Prduct Owner
PreCondition | Good Network Connection
Reference | Amazon
Test Scenario ID | Test Scenario Desription | Test Case ID | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Defect ID
TS21 | Verify the Customers UI | TCU1 | Check whether Customers is visible in side bar | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. View Customers option | Username: admin Password: admin@123 | Customers is visible in side bar | Customers is visible in side bar | Pass | N/A
|  | TCU2 | Check the response of customers drop down menu | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers | Username: admin Password: admin@123 | Customers drop down menu is visible in side bar | Customers drop down menu is visible in side bar | Pass | N/A
TS22 | Verify the Customer functionalities for Customers | TCU3 | Check the response of Customers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers | Username: admin Password: admin@123 | Customers list is opened | Customers list is opened | Pass | N/A
|  | TCU4 | Check whether customer name can be viewed in the aplhanumeric order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers | Username: admin Password: admin@123 | Customer name is sorted in alphanumeric order | Customer name is sorted in alphanumeric order | Pass | N/A
|  | TCU5 | Check response for the Filter functionality, admin has to enter the details of the Customer in order to fetch the customers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. Click on Filter | Username: admin Password: admin@123 Customer Name - venky testing Customer Group - Default Approved - Yes Date Added - 7/10/2021 E mail - venkytesting9@gmail.com Status - Enabled | Venky testing Customer is visible | Venky testing Customer is visible | Pass | N/A
|  | TCU6 | Check response for suggestions while filling the required fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers and fill the details 6. Click on Filter | Username: admin Password: admin@123 Customer Name - venky testing Customer Group - Default Approved - Yes Date Added - 7/10/2021 E mail - venkytesting9@gmail.com Status - Enabled | Suggestions are displayed when admin fills the fields | Suggestions are displayed when admin fills the fields | Pass | N/A
|  | TCU7 | Check whether even admin is able to fetch the customer when Customer name is entered in Uppercase | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. Click on Filter button | Username: admin Password: admin@123 Customer Name - VENKY TESTING Customer Group - Default Approved - Yes Date Added - 7/10/2021 E mail - venkytesting@9gmail.com Status - Enabled | Venky testing Customer is visible | Venky testing Customer is visible | Pass | N/A
|  | TCU8 | Check whether even admin is able to fetch the customer when Customer name is entered in lowercase | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. Click on Filter button | Username: admin Password: admin@123 Customer Name - venky testing Customer Group - Default Approved - Yes Date Added - 7/10/2021 E mail - venkytesting@9gmail.com Status - Enabled | venky testing Customer is visible | venky testing Customer is visible | Pass | N/A
|  | TCU9 | Check whether atleast one field is mandatory to get the exact detail of the Customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. Click on Filter button | Username: admin Password: admin@123 | Atleast one field should be mandatoy | Atleast one field should be mandatoy | Fail | DF10
|  | TCU10 | Check the function of Add New Button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. Click on Filter 7. In customer list click on add new button | Username: admin Password: admin@123 | Add Customer page is opened | Add Customer page is opened | Pass | N/A
|  | TCU11 | Check the response for mandatory fields in all the subtags under General | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - testing E- Mail - venkytesting9@gmail.com Telephone - 0987654321 Password - testing@123 confirm - testing@123 | Success: You have modified customers! | Success: You have modified customers! | Pass | N/A
|  | TCU12 | Check whether the created customer is added to the customer list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - testing E- Mail - venkytesting9@gmail.com Telephone - 0987654321 Password - testing@123 confirm - testing@123 | Created customer is added to the customer list after clicking on the save | Created customer is added to the customer list after clicking on the save | Pass | N/A
|  | TCU13 | Check the response for mandatory fields if First Name is not filled in the General subtag of Add customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Last Name - testing E- Mail - venkytesting9@gmail.com Telephone - 0987654321 Password - testing@123 confirm - testing@123 | Warning: Please check the form carefully for errors! First Name must be between 1 and 32 characters! | Warning: Please check the form carefully for errors! First Name must be between 1 and 32 characters! | Pass | N/A
|  | TCU14 | Check the response for mandatory fields if Last Name is not filled in the General subtag of Add customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - E- Mail - venkytesting9@gmail.com Telephone - 0987654321 Password - testing@123 confirm - testing@123 | Warning: Please check the form carefully for errors! Last Name must be between 1 and 32 characters! | Warning: Please check the form carefully for errors! Last Name must be between 1 and 32 characters! | Pass | N/A
|  | TCU15 | Check the response for mandatory fields if E-mail is not filled in the General subtag of Add customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - testing E- Mail - Telephone - 0987654321 Password - testing@123 confirm - testing@123 | Warning: Please check the form carefully for errors! E-Mail Address does not appear to be valid! | Warning: Please check the form carefully for errors! E-Mail Address does not appear to be valid! | Pass | N/A
|  | TCU16 | Check the response for mandatory fields if Telephone is not filled in the General subtag of Add customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - testing E- Mail - venkytesting9@gmail.com Telephone - Password - testing@123 confirm - testing@123 | Warning: Please check the form carefully for errors! Telephone must be between 3 and 32 characters! | Warning: Please check the form carefully for errors! Telephone must be between 3 and 32 characters! | Pass | N/A
|  | TCU17 | Check the response for mandatory fields if Password is not filled in the General subtag of Add customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - testing E- Mail - venkytesting9@gmail.com Telephone - 0987654321 Password - confirm - testing@123 | Warning: Please check the form carefully for errors! Password must be between 4 and 20 characters! | Warning: Please check the form carefully for errors! Password must be between 4 and 20 characters! | Pass | N/A
|  | TCU18 | Check the response for mandatory fields if Confirm is not filled in the General subtag of Add customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 First Name - Venky Last Name - testing E- Mail - venkytesting9@gmail.com Telephone - 0987654321 Password - testing@123 confirm - | Warning: Please check the form carefully for errors! Password must be between 4 and 20 characters! | Warning: Please check the form carefully for errors! Password must be between 4 and 20 characters! | Pass | N/A
|  | TCU19 | Check whether admin is able to edit the Customer details in Customer list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list click on add new button 7. Click on save | Username: admin Password: admin@123 | Admin is able to edit the Customer details in the Customer list | Admin is able to edit the Customer details in the Customer list | Pass | N/A
|  | TCU20 | Check whether admin is able to delete single exisiting customer | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list select single check box 7. Click on delete button | Username: admin Password: admin@123 | Single existing customer is deleted | Single existing customer is deleted | Pass | N/A
|  | TCU21 | Check whether admin is able to delete multiple exisiting customers | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customers 6. In customer list select multiple check boxes 7. Click on delete button | Username: admin Password: admin@123 | Multiple existing customers are deleted | Multiple existing customers are deleted | Pass | N/A
TS23 | Verify the Customers functionalities for customer groups | TCU22 | Check the response of customer groups | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups | Username: admin Password: admin@123 | Customer group list is visible | Customer group list is visible | Pass | N/A
|  | TCU23 | Check whether customer group name can be viewed in the aplhanumeric order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups | Username: admin Password: admin@123 | Customer Group name is sorted in alphanumeric order | Customer Group name is sorted in alphanumeric order | Pass | N/A
|  | TCU24 | Check the function of add new button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list click on add new | Username: admin Password: admin@123 | Add customer group page is opened | Add customer group page is opened | Pass | N/A
|  | TCU25 | Check the response for the form customer groups under add customer group | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list click on add new 7. Click on save | Username: admin Password: admin@123 | Admin is able to fill the Customer Group Name, Description, Approve New Customers and Sort Order fields in the add customer group page | Admin is able to fill the Customer Group Name, Description, Approve New Customers and Sort Order fields in the add customer group page | Pass | N/A
|  | TCU26 | Check the response for mandatory fields in all the subtags under add customer group | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list click on add new 7. Click on save | Username: admin Password: admin@123 Customer Group Name - testing123 | Success: You have modified customer groups! | Success: You have modified customer groups! | Pass | N/A
|  | TCU27 | Check whether the created customer group is added to the customer group list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list click on add new 7. Click on save | Username: admin Password: admin@123 Customer Group Name - testing123 | Created customer group is added to the customer group list after clicking on the save | Created customer group is added to the customer group list after clicking on the save | Pass | N/A
|  | TCU28 | Check the response for mandatory fields if Customer group name is not filled in the Add customer group page | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list click on add new 7. Click on save | Username: admin Password: admin@123 Customer Group Name - | Customer Group Name must be between 3 and 32 characters! | Customer Group Name must be between 3 and 32 characters! | Pass | N/A
|  | TCU29 | Check whether admin is able to edit the Customer group details in Customer group list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list click on add new 7. Click on save | Username: admin Password: admin@123 | Admin is able to edit the Customer group details in the Customer group list | Admin is able to edit the Customer group details in the Customer group list | Pass | N/A
|  | TCU30 | Check whether admin is able to delete single exisiting customer group | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list select single check box 7. Click on delete | Username: admin Password: admin@123 | Single existing customer group is deleted | Single existing customer group is deleted | Pass | N/A
|  | TCU31 | Check whether admin is able to delete multiple exisiting customers groups | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Customer groups 6.In customer group list select multiple check boxes 7. Click on delete | Username: admin Password: admin@123 | Multiple existing customer groups is deleted | Multiple existing customer groups is deleted | Pass | N/A
TCU32
TS24 | Verify the customers functionalities for Custom fields | TCU33 | Check the response of custom fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields | Username: admin Password: admin@123 | Custom field list is visible | Custom field list is visible | Pass | N/A
|  | TCU34 | Check whether customer field name can be viewed in the aplhanumeric order | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields | Username: admin Password: admin@123 | Customer Field name is sorted in alphanumeric order | Customer Field name is sorted in alphanumeric order | Pass | N/A
|  | TCU35 | Check the function of add new button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button | Username: admin Password: admin@123 | Add custom field page is opened | Add custom field page is opened | Pass | N/A
|  | TCU36 | Check the response for the form custom field under add custom fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button 7. Click on save | Username: admin Password: admin@123 | Admin is able to fill the Custom field name, Location, Type, customer group, Required, Status, Sort order and Custom field value name fields in the add custom field page | Admin is able to fill the Custom field name, Location, Type, customer group, Required, Status, Sort order and Custom field value name fields in the add custom field page | Pass | N/A
|  | TCU37 | Check the response for mandatory fields in all the subtags under add custom fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button 7. Click on save | Username: admin Password: admin@123 Custom field name - test Custom Field Value Name - testing Sort Order - 1 | Success: You have modified custom fields! | Success: You have modified custom fields! | Pass | N/A
|  | TCU38 | Check whether the created custom field is added to the custom field list after clicking on the save button | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button 7. Click on save | Username: admin Password: admin@123 Custom field name - test Custom Field Value Name - testing Sort Order - 1 | Created custom field is added to the custom field list after clicking on the save | Created custom field is added to the custom field list after clicking on the save | Pass | N/A
|  | TCU39 | Check the response for mandatory fields if Custom field name is not filled in the Add custom field page | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button 7. Click on save | Username: admin Password: admin@123 Custom field name - Custom Field Value Name - testing Sort Order - 1 | Custom Field Name must be between 1 and 128 characters! | Custom Field Name must be between 1 and 128 characters! | Pass | N/A
|  | TCU40 | Check the response for mandatory fields if Custom field value name is not filled in the Add custom field page | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button 7. Click on save | Username: admin Password: admin@123 Custom field name - test Custom Field Value Name - Sort Order - | Custom Value Name must be between 1 and 128 characters! | Custom Value Name must be between 1 and 128 characters! | Pass | N/A
|  | TCU41 | Check whether admin is able to edit the Custom field details in Custom field list | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list click on add new button 7. Click on save | Username: admin Password: admin@123 | Admin is able to edit the Custom field in the Custom field list | Admin is able to edit the Custom field in the Custom field list | Pass | N/A
|  | TCU42 | Check whether admin is able to delete single exisiting custom field | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list select single check box 7. Click on delete | Username: admin Password: admin@123 | Single existing custom field is deleted | Single existing custom field is deleted | Pass | N/A
|  | TCU43 | Check whether admin is able to delete multiple exisiting custom fields | 1. Navigate to http://retailm1.upskills.in/admin/ 2. Enter username and password 3. Click on Login 4. In side bar click on Customers 5. Click on Custom fields 6. In custom field list select multiple check boxes 7. Click on delete | Username: admin Password: admin@123 | Multiple existing custom fields is deleted | Multiple existing custom fields is deleted | Pass | N/A